**Technical/Scientific Contact Person : Charles Mockett**

**Organisation**  **:** CFD Software GmbH

Marie-Elisabeth-Lüders-Straße 1

10625 Berlin, Germany

Tel. +49-(0)30-590083320

E-mail: charles.mockett@cfd-berlin.com

**Quick Overview**

Please mark with an “X” in the red, yellow or green boxes how do you assess the present (general) status of your work:

(red = critical status, yellow = moderately problematic status, green = everything is running well)

**Timely according to DoW**

**Costs**

**Technical Progress**

**X**

**X**

**X**

**Please note:**

**When you have ticked yellow or red boxes, please explain problems you have encountered and possible solutions below:**

* Slight cost overrun due to high dissemination activities and unplanned additional coordination activities (e.g. test cases)
* …
* …

**Please double-click on the table to open Excel file**
**\*) Task Status: N = Not yet started, O = Ongoing, C = Completed**

**Summary of Activities**

Please describe concisely, for the actual quarter and task by task, e.g.:

*Work started, work performed, achievements, problems, dissemination activities, technical meetings managed and/or participated in, purchases, subcontracts, and what else is important for monitoring the project*

Task 1.1: Tech. coordination of project; Preparation of 12-month meeting.

Task 1.2: Feedback on website; Presentation of Go4Hybrid overview at ECFD VI conference; Presentation of Go4Hybrid results at North-German OpenFOAM User Meeting and ETMM10 Conference.

Task 2.1: Investigation of grid refinement for test case F2 (plane shear layer); Adjustment of hybrid convection scheme for new model variants.

Task 2.2: Finalisation of test case description for I5 round jet case; Further computations of I5 round jet case; Initial computations of I2 delta wing test case; Provision of grid & geom for I1 helicopter test case.

Task 3.1: not involved

Task 3.2: not involved

Task 4.1: Web meeting with UniMan to plan common assessment platform activities (e.g. common numerical & model setup)

Task 4.2: Not yet started