Technical/Scientific Contact Person	: 	Prof. Mikhail Strelets

Organisation					:	NTS

Krasnogo Kursanta, 5A

197198 St.-Petersburg, Russia

Tel. +7-812-3294791

E-mail: strelets@mail.rcom.ru

Quick Overview

Please mark with an “X” in the red, yellow or green boxes how do you assess the present (general) status of your work:

(red = critical status,  yellow = moderately problematic status,  green = everything is running well)

Please note:

When you have ticked yellow or red boxes, please explain problems you have encountered and possible solutions below:

- …

- …

- …

Please double-click on the table to open Excel file
*)  TaskStatus:  N = Not yet started,   O = Ongoing,   C = Completed

Summary of Activities

Please describe concisely, for the actual quarterand task by task, e.g.:

Work started, work performed, achievements, problems, dissemination activities, technical meetings managed and/or participated in, purchases, subcontracts, and what else is important for monitoring the project

Task 1.1:	Internal project management at NTS; participation in the Kickoff meeting in October 2013

Task 1.2:	Not yet started

Task 2.1:	A work on alternative definitions of SGS model length-scale for DES aimed at GAM and its assessment on generic flows (DIHT, BFS, round jet). One of proposed definitions is shown to ensure much weaker delay of the shear layer instability and much less sensitive of solution to the grid-spacing in the spanwise direction (see Figs. 1, 2 below).

Fig.1. Vorticity snapshot from SA DDES of BFS flow of Vogel and Eaton. Left: standard definition ; right: new definition

Fig.2. Effect of spanwise grid-spacing on distributions of mean friction from SA DDES of BFS flow of Vogel and Eaton.

Left: standard definition ; right: new definition

Task 2.2:	Not involved

Task 3.1:	Work on development of improved version of NTS Synthetic Turbulence Generator (STG) based on a volume source term. Computing the TC F1 (flat plate boundary layer) within zonal IDDES with the use of the current version of the STG (a benchmark for evaluation of further STG improvement(s)).

Task 3.2:	Preparing of flow description and guidelines (including mandatory grid) for TC I.4 (2D hump). It is demonstrated at the Kick-off meeting but not yet uploaded on the Project Web-site.

Task 4.1:	Not involved

Task 4.2:	Not yet started

# Text boxes

Timely according to DoW

Costs

Technical Progress

X

X

X