## Tabelle1
WORK SUMMARY - RISK MONITORING According to Quarterly Progress Reports QPR 01 - QPR 07 1 October 2013 to 30 June 2015
The table is considered to be (more or less) self-explanatory. However, a few remarks might be necessary: 1. All given figures are in person-months. 2. In the second column, "A" stands for "Actual" man-days used in the relevant quarter, "P" stands for the "Planned" effort in the relevant quarter, again in man-months. 3. The "Actual" figures are given per quarter and they are summed up per year and - in the last column - for the whole project working period. 4. The "Planned" man-days are specified according to the original values provided in the Technical Annex where they had been given as man-months per quarter. 5. Task-wise highlighted, written in Italic and underlined, partners are responsible for coordinating the corresponding task. 6. M1 to M6 are abbreviations for the Milestones defined in the Technical Annex. 7. The last page provides the total working days per partner - actual and planned 8. Coloring of the table has the following meaning:
Action item reached/fulfilled
Work on action item has started
Action item not yet started
Work load changes requested
Active period of task
Task 1.1 | Coordination of the project
Quarter | 1 | 2 | 1/2Y | 3 | 4 | 1Y | 5 | 6 | 3/2Y | 7 | 8 | 2Y | Total | Used | Planned | Rest | Remarks
Total
MILESTONES | M1 |  |  |  | M4 | [5 empty] | M8
CFDB | 0.25 | 0.2 | 0.45 | 0.15 | 0.15 | 0.3 | 0.25 | 0.25 | 0.5 | 0.15 |  | 0.15 | #REF! | 1.4 | 3 | 1.6
NTS | 0.05 | 0.05 | 0.1 | 0.05 | 0.05 | 0.1 | 0.02 | 0.01 | 0.03 | 0.01 |  | 0.01 | #REF! | 0.24 | 0.25 | 0.01
DLR | 0.05 | 0 | 0.05 | 0 | 0.05 | 0.05 | 0 | 0 | 0 | 0 |  | 0 |  | 0.1 | 0.25 | 0.15
FOI | 0.05 | 0 | 0.05 | 0.05 | 0 | 0.05 | 0.05 | 0 | 0.05 | 0.05 |  | 0.05 |  | 0.2 | 0.25 | 0.05
NLR | 0.06 | 0 | 0.06 | 0.06 | 0 | 0.06 | 0.06 | 0.06 | 0.12 | 0 |  | 0 |  | 0.24 | 0.25 | 0.01
ONERA | 0 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0.05 | 0.05 | 0.05 |  | 0.05 |  | 0.15 | 0.25 | 0.1
UniMAN | 0.05 | 0.05 | 0.1 | 0 | 0.05 | 0.05 | 0 | 0 | 0 | 0 |  | 0 | #REF! | 0.15 | 0.25 | 0.1
TOTAL | 0.51 | 0.35 | 0.86 | 0.31 | 0.3 | 0.61 | 0.38 | 0.37 | 0.75 | 0.26 | 0 | 0.26 | #REF! | 2.48 | 4.5 | 2.02
Task 1.2 | Web site / Dissemination / Exploitation
Quarter | 1 | 2 | 1/2Y | 3 | 4 | 1Y | 5 | 6 | 3/2Y | 7 | 8 | 2Y | Total | Used | Planned | Rest | Remarks
Total
MILESTONES | M1 |  |  |  | M4 | [5 empty] | M8
CFDB | 0.1 | 0.4 | 0.5 | 0.1 | 0.25 | 0.35 | 0.25 | 0.15 | 0.4 | 0.15 |  | 0.15 | #REF! | 1.4 | 1 | -0.4
NTS | 0 | 0.15 | 0.15 | 0.05 | 0 | 0.05 | 0 | 0 | 0 | 0.02 |  | 0.02 | #REF! | 0.22 | 0.25 | 0.03
DLR | 0 | 0 | 0 | 0 | 0.15 | 0.15 | 0.15 | 0 | 0.15 | 0 |  | 0 |  | 0.3 | 0.25 | -0.05
FOI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.05 | 0.05 |  | 0.05 |  | 0.1 | 0.25 | 0.15
NLR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0.25 | 0.25
ONERA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0.25 | 0.25
UniMAN | 0.8 | 0.4 | 1.2 | 0.1 | 0.05 | 0.15 | 0.1 | 0.05 | 0.15 | 0.2 |  | 0.2 | #REF! | 1.7 | 1.5 | -0.2
TOTAL | 0.9 | 0.95 | 1.85 | 0.25 | 0.45 | 0.7 | 0.5 | 0.25 | 0.75 | 0.42 | 0 | 0.42 | #REF! | 3.72 | 3.75 | 0.03
Task 2.1 | Non-zonal Methods: Development and evaluation for mandatory fundamental test cases
Quarter | 1 | 2 | 1/2Y | 3 | 4 | 1Y | 5 | 6 | 3/2Y | 7 | 8 | 2Y | Total | Used | Planned | Rest | Remarks
Total
MILESTONES |  | M2 |  |  |  |  | M5
CFDB | 0.65 | 2 | 2.65 | 1.5 | 0.5 | 2 | 0.1 | 0.25 | 0.35 | 0 |  | 0 | #REF! | 5 | 4.5 | -0.5
NTS | 1.5 | 0.5 | 2 | 0 | 2 | 2 | 0.5 | 0.5 | 1 | 0.5 |  | 0.5 | #REF! | 5.5 | 3 | -2.5
FOI | 0.45 | 0.75 | 1.2 | 0.5 | 0.5 | 1 | 2 | 0.8 | 2.8 | 0.86 |  | 0.86 |  | 5.86 | 6 | 0.14
NLR | 0.43 | 0.69 | 1.12 | 1.25 | 0.7 | 1.95 | 0 | 0 | 0 | 0.2 |  | 0.2 |  | 3.27 | 3 | -0.27
ONERA | 0 | 0.25 | 0.25 | 0.75 | 0.75 | 1.5 | 1 | 0.2 | 1.2 | 0.05 |  | 0.05 |  | 3 | 3 | 0
TOTAL | 3.03 | 4.19 | 7.22 | 4 | 4.45 | 8.45 | 3.6 |  | 5.35 |  |  |  | #REF! | 21.02 | 19.5 | -3.13
Task 2.2 | Non-zonal Methods: Demonstration of improvements based on complex test cases
Quarter | 1 | 2 | 1/2Y | 3 | 4 | 1Y | 5 | 6 | 3/2Y | 7 | 8 | 2Y | Total | Used | Planned | Rest | Remarks
Total
MILESTONES | [6 empty] | M5 |  |  |  | M8
CFDB |  |  |  | 0.5 | 1.25 | 1.75 | 0.2 | 0.8 | 1 | 0.5 |  | 0.5 | #REF! | 3.25 | 3 | -0.25
NTS |  | 1.2 | 1.2 |  | 1.3 | 1.3 | 1.5 | 1.3 | 2.8 | 1.3 |  | 1.3 |  | 6.6 | 0 | -6.6
FOI |  |  |  |  | 0 | 0 | 0.05 | 2.05 | 2.1 | 1 |  | 1 |  | 3.1 | 4 | 0.9
NLR |  |  |  |  | 0.5 | 0.5 | 1.5 | 1.1 | 2.6 | 1.4 |  | 1.4 |  | 4.5 | 4 | -0.5
TOTAL |  | 1.2 | 1.2 | 0.5 | 3.05 | 3.55 | 3.25 | 5.25 | 8.5 | 4.2 | 0 | 4.2 | #REF! | 17.45 | 11 | -6.45
Task 3.1 | Embedded Methods: Development and evaluation for mandatory fundamental test cases
Quarter | 1 | 2 | 1/2Y | 3 | 4 | 1Y | 5 | 6 | 3/2Y | 7 | 8 | 2Y | Total | Used | Planned | Rest | Remarks
Total
MILESTONES |  | M2 |  |  |  |  | M5
#REF!
NTS | 1.5 | 1 | 2.5 | 2 | 0.2 | 2.2 | 0 | 1 | 1 | 1 |  | 1 | #REF! | 6.7 | 6 | -0.7
DLR | 0.25 | 1.5 | 1.75 | 1.5 | 2 | 3.5 | 1.25 | 0.75 | 2 | 0 |  | 0 |  | 7.25 | 7.5 | 0.25
0
ONERA | 0.5 | 1.5 | 2 | 0.5 | 1 | 1.5 | 0.5 | 0.5 | 1 | 0.4 |  | 0.4 |  | 4.9 | 5 | 0.1
UniMAN | 0.2 | 1 | 1.2 | 1 | 0.5 | 1.5 | 1 | 0.1 | 1.1 | 0.1 |  | 0.1 |  | 3.9 | 6 | 2.1
TOTAL | 2.45 | 5 | 7.45 | 5 | 3.7 | 8.7 | 2.75 | 2.35 | 5.1 |  |  |  | #REF! | 21.25 | 24.5 | 1.75
Task 3.2 | Embedded Methods: Demonstration of improvements based on complex test cases
Quarter | 1 | 2 | 1/2Y | 3 | 4 | 1Y | 5 | 6 | 3/2Y | 7 | 8 | 2Y | Total | Used | Planned | Rest | Remarks
Total
MILESTONES | [6 empty] | M5 |  |  |  | M8
NTS | 1 |  | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 1 |  | 1 |  | 4 | 8 | 4
DLR |  |  |  | 0.25 | 0.25 | 0.5 | 0.75 | 1.25 | 2 | 2 |  | 2 |  | 4.5 | 5 | 0.5
ONERA |  |  |  | 0.5 | 0 | 0.5 | 0.5 | 1.25 | 1.75 | 1.95 |  | 1.95 |  | 2.45 | 5 | 2.55
UniMAN |  |  |  | 0.1 | 0.1 | 0.2 | 0.1 | 0.2 | 0.3 | 0.2 |  | 0.2 |  | 5.65 | 2 | -3.65
TOTAL | 1 |  | 1 | 2.85 | 0.35 | 3.2 | 1.35 | 2.7 | 4.05 | 5.15 | 0 | 5.15 | 0 | 13.4 | 20 | 3.4
Task 4.1 | Common Assessment Platform
Quarter | 1 | 2 | 1/2Y | 3 | 4 | 1Y | 5 | 6 | 3/2Y | 7 | 8 | 2Y | Total | Used | Planned | Rest | Remarks
Total
MILESTONES | [6 empty] | M5 |  |  | M7
CFDB |  |  |  |  | 0.25 | 0.25 | 0.4 | 1 | 1.4 | 2 |  | 2 | #REF! | 3.65 | 3 | -0.65
UniMAN |  |  |  |  | 0.25 | 0.25 | 0.6 | 2.4 | 3 | 1.5 |  | 1.5 | #REF! | 4.75 | 2.5 | -2.25
TOTAL |  |  |  |  | 0.5 | 0.5 | 1 | 3.4 | 4.4 | 3.5 | 0 | 3.5 | #REF! | 8.4 | 5.5 | -2.9
Task 4.2 | Best-practice, knowledge preservation, and workshop preparation
Quarter | 1 | 2 | 1/2Y | 3 | 4 | 1Y | 5 | 6 | 3/2Y | 7 | 8 | 2Y | Total | Used | Planned | Rest | Remarks
Total
MILESTONES | [6 empty] | M5 | M6 |  |  | M8
CFDB | [6 empty] | 0.1 | 0.25 | 0.35 | 1.25 |  | 1.25 | #REF! | 1.6 | 1.5 | -0.1
NTS | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | #REF! | 0 | 0.5 | 0.5
DLR | [6 empty] | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 1 | 1
FOI | [6 empty] | 0 | 0 | 0 | 0.16 |  | 0.16 |  | 0.16 | 0.5 | 0.34
NLR | [6 empty] | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0.5 | 0.5
ONERA | [6 empty] | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0.5 | 0.5
UniMAN | [6 empty] | 0 | 0 | 0 | 0.1 |  | 0.1 | #REF! | 0.1 | 1 | 0.9
TOTAL | [6 empty] | 0.1 | 0.25 | 0.35 | 1.51 | 0 | 1.51 | #REF! | 1.86 | 5.5 | 3.64
TOTAL
Quarter | 1 | 2 | 1/2Y | 3 | 4 | 1Y | 5 | 6 | 3/2Y | 7 | 8 | 2Y | Total | Used | Planned | Rest | Remarks
Total
CFDB | 1 | 2.6 | 3.6 | 2.25 | 2.4 | 4.65 | 1.3 | 2.7 | 4 | 4.05 | 0 | 4.05 | #REF! | 16.3 | 16 | -0.3
NTS | 4.05 | 2.9 | 6.95 | 4.1 | 3.55 | 7.65 | 2.02 | 2.81 | 4.83 | 3.83 | 0 | 3.83 | #REF! | 23.26 | 18 | -5.26
DLR | 0.3 | 1.5 | 1.8 | 1.75 | 2.45 | 4.2 | 2.15 | 2 | 4.15 | 2 | 0 | 2 |  | 12.15 | 14 | 1.85
FOI | 0.5 | 0.75 | 1.25 | 0.55 | 0.5 | 1.05 | 2.1 | 2.9 | 5 | 2.12 | 0 | 2.12 |  | 9.42 | 11 | 1.58
NLR | 0.49 | 0.69 | 1.18 | 1.31 | 1.2 | 2.51 | 1.56 | 1.16 | 2.72 | 1.6 | 0 | 1.6 |  | 8.01 | 8 | -0.01
ONERA | 0.5 | 1.8 | 2.3 | 1.75 | 1.75 | 3.5 | 2 | 2 | 4 | 2.45 | 0 | 2.45 |  | 12.25 | 14 | 1.75
UniMAN | 1.05 | 1.45 | 2.5 | 1.2 | 0.95 | 2.15 | 1.8 | 2.75 | 4.55 | 2.1 | 0 | 2.1 | #REF! | 11.3 | 13.25 | 1.95
TOTAL | 7.89 | 11.69 | 19.58 | 12.91 | 12.8 | 25.71 | 12.93 | 14.57 | 29.25 | 15.04 | 0 | 15.04 | #REF! | 89.58 | 94.25 | 4.67
Start until now QPR-3 | Technical Progress |  |  | Costs |  |  | Timely according to DoW
CFDB | [10 empty] | Cost overrun in WP1 due to high dissemination activities and unplanned additional coordination activities (e.g. test cases) Delay in compilation of D4.2-18 – no impact on final project results expected.
NTS
DLR
FOI
NLR
ONERA
UniMAN